## Project Status
Project | Workstream | Planned % | Actual % | Budget USD | Actual Spend USD | Risk | Status | Owner
ERP Transformation | Technology | 72 | 68 | 4200000 | 3950000 | High | At Risk | Priya Shah
Supply Chain Excellence | Operations | 60 | 63 | 2800000 | 2450000 | Medium | On Track | Arjun Mehta
Finance Process Transformation | Finance | 55 | 49 | 1900000 | 1720000 | High | At Risk | Neha Kapoor
Data & Analytics Enablement | Data | 45 | 42 | 2300000 | 1280000 | Medium | On Track | Rahul Verma
Customer Experience | Customer | 38 | 41 | 1600000 | 1510000 | Low | On Track | Ananya Rao
Plant Productivity | Operations | 66 | 58 | 3100000 | 3010000 | High | At Risk | Vikram Singh
Cyber Resilience | Technology | 50 | 52 | 2500000 | 1190000 | Medium | On Track | Karan Bhatia
Workforce Transformation | People | 40 | 35 | 1400000 | 980000 | Medium | At Risk | Meera Iyer
Sustainability Reporting | ESG | 30 | 34 | 1100000 | 760000 | Low | On Track | Sonal Jain
Procurement Optimization | Finance | 48 | 44 | 1750000 | 1320000 | Medium | At Risk | Amit Malhotra

## Resource Utilization
Consultant | Project | Role | Allocated Hours | Actual Hours | Utilization %
A Kumar | ERP Transformation | PM | 420 | 455 | 108
S Rao | ERP Transformation | Business Analyst | 520 | 610 | 117
R Gupta | Supply Chain Excellence | Consultant | 480 | 455 | 95
M Thomas | Finance Process Transformation | PM | 390 | 445 | 114
P Singh | Data & Analytics Enablement | Data Consultant | 510 | 485 | 95
N Jain | Customer Experience | Consultant | 360 | 340 | 94
K Das | Plant Productivity | Operations Consultant | 450 | 505 | 112
T Roy | Cyber Resilience | Risk Consultant | 400 | 390 | 98
V Menon | Workforce Transformation | Change Consultant | 380 | 420 | 111
L Shah | Procurement Optimization | Procurement Consultant | 410 | 455 | 111

## Risks & Issues
Project | Risk / Issue | Category | Severity | Probability | Owner | Status
ERP Transformation | Integration defects may delay testing | Technology | High | High | Priya Shah | Open
Finance Process Transformation | Process requirements remain unresolved | Scope | High | High | Neha Kapoor | Open
Plant Productivity | Downtime reduction below business case | Benefits | High | High | Vikram Singh | Open
Procurement Optimization | Supplier data quality inconsistent | Data | Medium | High | Amit Malhotra | Mitigation
Data & Analytics Enablement | Data ownership unclear | Governance | Medium | High | Rahul Verma | Open
Cyber Resilience | Legacy systems require compensating controls | Security | High | Medium | Karan Bhatia | Monitoring